## New Construction Schedule
BuildMyHouse.com ©
Overall Progress: 0%
Id | Level | Name | Progress | Start | Due | Contact | Completion Date | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | Baseline: Start Date | Baseline: Due Date | Duration (Cal. Days) | Working Days | Tags | - | - | - | - | - | - | - | - | - | -
1 | 1 | Design & Planning: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.1 | 2 | Create Floorplan Sketch | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.2 | 2 | Designer Draft 1 | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.3 | 2 | Review Draft 1 | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.4 | 2 | Designer Draft 1 Corrections | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.5 | 2 | Obtain Building Permits | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.6 | 2 | Get surveyor to draw site plan & stake lot? | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.7 | 2 | Get Subcontractor Bids | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
1.8 | 2 | Purchase Construction & General Liability Insurance | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
2 | 1 | Lot Preparation: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
2.1 | 2 | Mark Utilties | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
2.2 | 2 | Scrape Lot to clear Vegetation | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
2.3 | 2 | Stake Foundation & Lot Lines | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
| 2 | Set Up Temporary Power |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3 | 1 | Foundation: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.1 | 2 | Excavate Footings | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.2 | 2 | Footing Inspection | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.3 | 2 | Pour Footings | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.4 | 2 | Build Stem walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.5 | 2 | Fill CMU block cores with concrete | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.6 | 2 | Install Under Slab Plumbing Lines | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.7 | 2 | Install Under Slab Electrical Conduit | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.8 | 2 | Install Radon Mitigation System | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.9 | 2 | Pre-treat Soil for Termites | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.10 | 2 | Install under slab Gravel Bed | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.11 | 2 | Install Vapor Barrier Under Slab | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.12 | 2 | Install Slab Rebar | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.13 | 2 | Install Radiant Heat Pex Tubing & Manifolds | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.14 | 2 | Pour Slab | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.15 | 2 | Cure Slab | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
3.16 | 2 | Termite Seal Slab Penetrations | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4 | 1 | Framing: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.1 | 2 | Layout the walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.2 | 2 | Build the floor system | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.2a | 3 | Install Sill Gasket, Termite Barrier & Sill Plate | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.2b | 3 | Install Floor Joists | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.2c | 3 | Install rim joists | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.2d | 3 | Install subflooring | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.3 | 2 | Frame the Exterior Walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.3a | 3 | Assemble wall sections | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.3b | 3 | Raise the walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.3c | 3 | Install sheathing | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.4 | 2 | Frame the Interior Walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.5 | 2 | Install Roof Trusses and roof sheating | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.6 | 2 | Install Windows & Exterior Doors | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.7 | 2 | Install Weather Resistant Barrier | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.8 | 2 | Spray Boracare on interior wall voids | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
4.9 | 2 | Install Window Flashing | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5 | 1 | Rough HVAC, Plumbing & Electrical: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.1 | 2 | Connect gas lines | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.2 | 2 | Install ERV Ducts & Makeup Air | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.3 | 2 | Finish Plumbing Rough in | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.4 | 2 | Electrical Rough-in | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.5 | 2 | Low Voltage Rough In | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.6 | 2 | Install fire systems & alarms | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.7 | 2 | Install fireplace vents and unit | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.8 | 2 | Central Vacuum Rough-in | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.9 | 2 | Install Radiant Heat | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.9a | 3 | Gyp-crete if needed | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.9b | 3 | Floor Protection over radiant heat if no gyp-crete | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.11 | 2 | Rough in inspections | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.11a | 3 | HVAC Rough-In Inspection | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.11b | 3 | Electrical Rough-In Inspection | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
5.11c | 3 | Plumbing Rough-in Inspection | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6 | 1 | Roofing: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.1 | 2 | Install roof decking | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.2 | 2 | Install drip edge | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.3 | 2 | Install underlayment | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.4 | 2 | Install roof flashing | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.5 | 2 | Install roof material (shingles, standing seam etc. | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.6 | 2 | Install ridge vents | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.7 | 2 | Install ridge cap shingles or trim | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
6.8 | 2 | Install fascia & soffits | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
7 | 1 | Siding: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
7.1 | 2 | Install siding material | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
7.2 | 2 | Paint and caulk as needed | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
7.3 | 2 | Add exterior trim | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
7.4 | 2 | Install gutters | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8 | 1 | Air Sealing Drywall & Insulation: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.1 | 2 | Install gaskets for Drywall | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.2 | 2 | Install Attic Eve Baffles | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.3 | 2 | Air seal exterior wall penetrations | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.4 | 2 | Air seal all electrical boxes | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.5 | 2 | Insulate Master tub and hall shower | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.6 | 2 | Foam insulation on exterior of bonus room | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.7 | 2 | Insulate skylight shafts | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.8 | 2 | Spray foam walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.9 | 2 | Insulation Inspection | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.10 | 2 | Drywall Ceiling | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.11 | 2 | Air seal ceiling penetrations | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.12 | 2 | Drywall interior | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
8.13 | 2 | Blow Cellulose in Attic | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9 | 1 | Paint: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9.1 | 2 | Prime Interior Walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9.2 | 2 | Paint interior walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9.3 | 2 | Deliver Interior Trim | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9.4 | 2 | Prime interior Trim | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
9.5 | 2 | Paint Interior trim first coat | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.1 | 1 | Cabinetry | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.2 | 2 | Install built-in cabinetry (may switch with tile or flooring if required) | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.3 | 2 | install kitchen & laundry cabinets | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.4 | 2 | install bathroom vanities | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.5 | 2 | Install built-ins throughout the house | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
10.6 | 2 | Install closet systems | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
11 | 1 | Tile & Interior Masonry | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
11.1 | 2 | Tile floors | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
11.2 | 2 | Build Shower Pans | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
11.3 | 2 | Tile shower walls | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
11.4 | 2 | Tile backsplashes if cabinets are in | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12 | 1 | Flooring: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.1 | 2 | Acclimate flooring if needed | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.2 | 2 | Install vapor barrier or underlayment (if needed) | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.3 | 2 | Install Hardwood, LVP, Engineered or Carpet | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.4 | 2 | Install transition strips | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.5 | 2 | Protect floor as needed | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13 | 1 | Interior Trim and Doors: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.1 | 2 | Install interior doors | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.2 | 2 | Install Interior Trim | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.3 | 2 | Install Kitchen Cabinets (if installed over floors) | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.4 | 2 | Install Bathroom Cabinents (if installed over floors) | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.5 | 2 | Install counter tops | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.6 | 2 | Install kitchen appliances | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.7 | 2 | Install door and cabinet hardware | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.8 | 2 | Install bathroom hardware | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12 | 1 | HVAC Trim Out: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
12.1 | 2 | Install airconditioner | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13 | 1 | Plumbing Trim Out: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.1 | 2 | Install tub & showers | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.2 | 2 | Install toilets and faucets | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
13.3 | 2 | Install water heater | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
14 | 1 | Electrical Trim Out: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
14.1 | 2 | Install switches and plugs | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
14.2 | 2 | Install light fixtures | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
14.3 | 2 | Install smoke detectors |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
14.4 | 2 | Install door cameras or door bell |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15 | 1 | Landscaping: | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.1 | 2 | Install front porch | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.2 | 2 | Install Driveway | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.3 | 2 | Install sprinkler system | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.4 | 2 | Install front sidewalk | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.5 | 2 | Sod front and sides | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -
15.6 | 2 | Seed back yard | 0% |  |  |  | - | - | - | - | - | - | - | - | - | - | - | -